## Test Scenarios
Security Service FCU- 202X FIS Upgrade - HX Regression Testing
|  | Project Manager |  | Jim Powell
|  | Business Analyst |  | Deidre Cox
Environment
Testing Start Date
Testing End Date
Test Case ID | RSEC/Regression | Description | Test Feature | Precondition/Data | Steps to Execute | Expected Results | Screen Shot | Pass | Fail | Tested By | Retest Date | Defect/Comments
Regression
1 | Regression | HXB1- HX Process Control | Update the HX Control Record |  | 1. Input HXB1 (transmit) 2. Input CTL1= 10 (transmit) 3. Tab to Holidays, enter Holidays Dates for Month (transmit) | Validate that Holidays were accepted. Note: cannot fill the Holidays, need to leave last Holiday MMDDYY. | #VALUE!
2 | Regression | HX01- Add | Add a new Citizen HX Record |  | 1. Input HX01 (transmit) 2. Enter CTL1= 10, and Action = A (transmit) 3. Enter Name, TIN, TIN TYPE, TIN CTF, B Notice Date, B NTC TAX YR, , ACT=A, MNT = Y, APPL and APPLICATION ACCOUNT NUMBER = 100000000000+10 digit IM Acct Number, DT Opened (for account) (transmit) | Validate that the HX record is created, and applicable fields are set. Appl Opened will populate from DT Opened of APPL ACCOUNT, 3 year period will calculate 12/31/YY from B NTC TAX YR
3 | Regression | HX01- Delete | Delete an existing HX Record | Identify Existing HX Record | 1. Input HX01 (transmit) 2. Enter CTL1= 10, Account = Valid HX Account Number, and Action = D (transmit) 3. Tab to "Enter D to Delete P to Purge"- Enter D (transmit) 4. Input HX01 (transmit) 5. Input CTL1 = 10 and Account = Same Account Number (transmit) | Validate that the status has been changed to 4- Delete.
4 | Regression | HX01- Update | Updating existing HX Record | Identify Existing HX Record | 1. Input HX01 (transmit) 2. Enter CTL1= 10, Account = Valid HX Account Number, and Action = U, (transmit). 3. Tab to W-9 Sent" and enter Date (more current) (transmit) 4. Input HX01 (transmit) 5. Input CTL1 = 10 and Account = Same Account Number (transmit) | Validate that the W-9 Sent date has updated correctly.
5 | Regression | HX01- Inquiry | Inquiring on an existing HX Record | Identify Existing HX Record | 1. Input HX01 (transmit) 2. Enter CTL1= 10, Account = Valid HX Account Number, and Action = Blank, (transmit). | Validate that the correct record is returned.
6 | Regression | HX72 - Add | Adding a new C Notice Record |  | 1. Input HX72 (transmit) 2. Enter CTL1= 10, and Action = A (transmit) 3. Enter Name, TIN, Adress, City, State Zip Code, C-Notice Date, Account Number, and TCC - 18288 (transmit ) 4. input HX72 (transmit) 5. Input CTL1 = 10, and Name or TIN of record added (transmit) | Validate that the record has been created and is returned.
7 | Regression | HX72 - Delete | Deleting an existing C Notice Record | Identify Existing C-Notice Record | 1. Input HX72 (transmit) 2. Enter CTL1= 10, and Action = D (transmit) 3. Enter Name or TIN (transmit) 4. Tab to "Enter Y to Delete" Enter Y (transmit) 5. input HX72 (transmit) 6. Input CTL1 = 10, and Name or TIN of record deleted (transmit) | Validate that the record is not returned.
8 | Regression | HX72 - Update | Updating an existing C Notice Record | Identify Existing C-Notice Record | 1. Input HX72 (transmit) 2. Enter CTL1= 10, and Action = U (transmit) 3. Enter Name or TIN (transmit) 4. Tab to Address and change Street Addres (transmit) 5. input HX72 (transmit) 6. Input CTL1 = 10, and Name or TIN of record updated (transmit) | Validate that the record has been updated with the new street address.
9 | Regression | HX72 - Inquiry | Inquiring in an existing C Notice Record | Identify Existing C-Notice Record | 1. Input HX72 (transmit) 2. Enter CTL1= 10, and Action = I (transmit) 3. Enter Name and TIN (transmit) | Validate that correct record is returned.
10 | Regression | HX01- Add | Add a new NRA HX Record |  | 1. Input HX01 (transmit) 2. Enter CTL1= 10, and Action = A (transmit) 3. Enter Name, TIN, TIN TYPE = 8, TIN CTF =, ACT=A, MNT = Y, APPL and APPLICATION ACCOUNT NUMBER = 100000000000+10 digit IM Acct Number, DT Opened (for account) (transmit) | Validate that the HX record is created, and applicable fields are set. Appl Opened will populate from DT Opened of APPL ACCOUNT, DATE NEXT 3 year period will calculate 01/02/YY from YEAR of CERT DATE
11 | Regression | IM or ST to HX HX to IM or ST | Open a New Account for NRA |  | 1. Open a new IM account through RMSA - When creating Member set the following fields: Update W-9 Cert to 8 Update Citizen/Alien to 1 Update Fed Rate Ptr to 002 Update Tax Country to MX Update to W-8 Cert to 1 Update W-8 Type to 1 Update Fatca Exempt to 15 Update Foreign Tax: Tax Code to 2 , and Tax ID to 1234567890 | Validate that the Maintained Fields were updated. After-Batch validate that Account Detail appears on the HX03TPRT - New Account Trailer and Print Validate that the Maintenance Back to the Application appears on the HX41NA - Generated Trans Journal. Maintenance is HX Account Number, sent with an After-Post flag. After 2nd Batch - Validate that the Account has been updated with the HX Account Number - IMI1 screen page 2.
12 | Regression | IM or ST to HX HX to IM or ST | Update an Existing Account for NRA | Identify an Existing IM Account that is not currently set as NRA | 1. Input IMI1 (enter) 2. Input Account Number (enter) 3. Input IM2T (enter) 4. Update W-9 Cert to 8 5. Update Citizen/Alien to 1 6. Update Fed Rate Ptr to 002 7. Update Tax Country to MX 8. Update to W-8 Cert to 1 9. Update W-8 Type to 1 10. Update Fatca Exempt to 15 11. Update Foreign Tax: Tax Code to 2 , and Tax ID to 1234567890 (enter) | Validate that the Maintained Fields were updated. After-Batch validate that Account Detail appears on the HX03TPRT - New Account Trailer and Print Validate that the Maintenance Back to the Application appears on the HX41NA - Generated Trans Journal. Maintenance is HX Account Number, sent with an After-Post flag. After 2nd Batch - Validate that the Account has been updated with the HX Account Number - IMI1 screen page 2.
QA Testing
1
2
3
4 | [6 empty] | 9
5
6
7
8
9
10
11
12
13
14
15
16
17 | [6 empty] | AN INVALID VALUE WAS ENTERED IN A CUSTOMER USER FIELD. FOR A LIST OF VALID VALUES, POSITION YOUR CURSOR ON THE FIELD AND PRESS PF12 TO ACCESS ONLINE HELP FOR THAT FIELD.
18
19
20

## Screenshots
Test Case ID | RSEC | Test Feature | Screen Shot
1 |  | HXB1- HX Process Control
2 |  | HX01- Add
3 |  | HX01- Delete
4 |  | HX01- Update
5 |  | HX01- Inquiry
6 |  | HX72 - Add
7 |  | HX72 - Delete
8 |  | HX72 - Update
9 |  | HX72 - Inquiry
10 |  | HX01
11 |  | Open New HX Acct from Application New Account
12 |  | Open New HX Acct from Application Maintenance
9
RMUF
AN INVALID VALUE WAS ENTERED IN A CUSTOMER USER FIELD. FOR A LIST OF VALID VALUES, POSITION YOUR CURSOR ON THE FIELD AND PRESS PF12 TO ACCESS ONLINE HELP FOR THAT FIELD.

## Screen Comparison
Screen Name | Screen Description | PROD Screen | Result | Result | UAT4 2nd round | Result
HXBN - HX Paper B-Notice Entry | To add, update, or delete a paper IRS B-Notice (Invalid TIN).
HXB1 - Process Control (Prompt) | To access the Process Control detail screen to add, delete, or update a Process Control Record (PCR).
HXB1 - Process Control | To add or update a Process Control Record (PCR). |  |  | Correct
HXMN - Certification Tracking Menu | To access the following screens: HXRF - Cross-Reference Inquiry HX01 - Account Add/Maintenance/Delete HXB1 - Process Control HXR1 - Report Control HXTB - TIN/Name Browse Inquiry HX72 - C-Notice Maintenance HXBN - HX Paper B Notice Entry
HXRF- Cross Referencve Inquiry (Prompt) | To inquire about accounts in the HX Account Master File
HXRF - Application Account Number inquiry | To display the listings for any selection by product account (Type 05).
HXRF-TIN Inquiry | To display the listings for any selection by TIN (Types 01 and 02)
HXRF - Name Inquiry | To display the listings for any selection by Name (Types 03 and 04).
HXR1- Report Control (Prompt) | To access the Report Control detail screen to select processing options for reports and notices.
HXR1 - Report Control | To change report information
HXTB - TIN/NAME Browse (Prompt) | To access the TIN/Name Browse detail screen.
HXTB- TIN Browse | To display the listings matching the TIN entered on the prompt screen.
HXTB-Name Browse | To display the listings matching the name entered on the prompt screen.
HX01- Maint/Inquiry (Prompt) | To access or delete a citizen or nonresident alien (NRA) account.
HX01- Citizen Maint/inquiry | To add, update, or inquire about an HX citizen account.
HX01- NRA Maint/Inquiry | To add, update, or inquire about an HX nonresident alien (NRA) account.
HX01- Citizen Delete/Purge | To delete or purge an HX citizen account.
HX01- NRA Delete/Purge | To delete or purge an HX NRA account.
HX72- C-Notice Maintenance (Prompt) | To add, delete, update, or inquire about a C-Notice (Underreported) account.
HX72- C-Notice Maintenance | To add, delete, update, or inquire about a C-Notice (Underreported) account.

## Reports Testing
Report Name | Report Description | Frequency | Critical to LOB | Precondition | IN PROD? | Pass DEV4 | Fail Dev4 | Pass UAT4 | Fail UAT4 | Pass QA | Fail QA | Untestable | Defect/Comments
FIHXRP01 | Online Account Transaction Journal | Event Driven
HX07LOAD | HX TIN Browse Load | Daily
HX07ST | HX07 Extract Report- ST | Daily
HX07ST | HX07 Extract Report- ST Totals | Daily
HX02IM | HX02 Extract Report - IM | Daily
HX02ST | HX02 Extract Report - ST | Daily
HX03 | Extract Edit and Cross-Reference Serach | Daily
HX03TPRT | New Account and Trailer Print | Daily
HX04 | IRS B-Notice Match Summary | Event Driven
HX04RPT | IRS Notice Match Detail | Event Driven
HX04APND | HX PCR/IRS Payer EIN Match | Event Driven
HX07IM | HX07 Extract Report- IM | Daily
HX07IM | HX07 Extract Report- IM Totals | Daily
HX07LOAD | HX TIN Browse Load | Daily
HX14 | Process control Record Report | Daily
HX31 | Data Header print | Daily
HX31 | Processing Totals | Daily
HX41ML | Master Listing | Daily
HX41ML | Master Listing | Daily
HX41NA | Generated Tran Journal | Event driven
HX41NB | Notice Journal - By Account | Daily
HX41NC | Notice Journal- By Ntc | Daily
HX41PC | W9 TIN Cert Request | Event Driven
HX41PF | IRS Invalid TIN Notice (B-Notice) | Event Driven/File from IRS
HX41PG | IRS Second Invalid TIN Notice (2nd B-Notice) | Event Driven/File from IRS
HX41RA | NRA Certifications Due/Past Due Report | Daily
HX41RB | Citizens Awaiting TIN Report | Daily
HX41RC | Accounts without Trailers Report | Daily
HX42 | Report Exception Register | Daily
HX72 | C-Notice Match Report | Weekly- Tuesday
HX72 | C-Notice Processing Totals | Weekly- Tuesday
HX72IMTB | C-Notice IMPACs Extract Report | Weekly- Tuesday
HX72IMTB | C-Notice IMPACs Extract Totals | Weekly- Tuesday
HX72RFEX | C-Notice Cross Reference Extract Report | Weekly- Tuesday
HX72RFLD | C-Notice Cross Reference Load Report | Weekly- Tuesday
HX72RFLD | C-Notice Cross Reference Load Report | Weekly- Tuesday
HX72RPT | C-Notice File Report | Weekly- Tuesday
HX72RPT | C-Notice File Report Totals | Weekly- Tuesday
HX72STTB | C-Notice Savings/Time Extract Report | Weekly- Tuesday
HX72STTB | C-Notice Savings/Time Extract Totals | Weekly- Tuesday
HX72TBLD | C-Notice TIN/NAME Browse Load Report | Weekly- Tuesday
HX72TBLD | C-Notice TIN/NAME Browse Load Totals | Weekly- Tuesday
HXRFLOAD | HX XREF Load (Totals) | Daily
HX REPORTS ARE LOCATED IN MY DOCS UNDER COMPLIANCE

## Misc
B-Notice Test
- Test with PROD Processing (Oct/Nov)
FIDM Test
- Test using copy of PROD files
Runs Qrtly, Feb/May, Aug, Nov
TEXAS HB-1258 Test
- Test using copy of Prod file
Runs Qrtly, Feb/May, Aug, Nov